## Detailed UI Tasks & Estimates
Travelpeek - UI Implementation Task Breakdown & Time Estimation
Page / Section | Feature / Component | Micro-Task Title | Detailed UI Task Description | Estimated Hours | Complexity | Styling / Elements
Home Page | Hero Section | Search Input Box | HTML structure, rounded borders, shadow effects, placeholder styling. | 1.1 | Low | HTML, SCSS border-radius, box-shadow
Home Page | Hero Section | Suggestion Pills | Horizontal flex-wrap layout, padding and spacing of the suggested queries tags. | 0.39 | Low | Flexbox wrap, gap alignment, query pills
Home Page | Hero Section | Pills Hover States | SCSS transitions on query pills (light gray hover background, color shifts). | 0.39 | Low | CSS transitions, hover effects
Home Page | Curated For You | Title & View All Link | Heading styling (40px bold), letter spacing (-0.4px) and blue arrow link positioning. | 0.55 | Low | Display font styling, align-items-end flex
Home Page | Curated For You | Responsive Grid Layout | CSS grid/flexbox setup for 4-column card row that wraps cleanly to tablet/mobile. | 0.55 | Medium | Bootstrap grid, flex-direction column
Home Page | Curated For You | Card Base Container | Card container border-radius (16px), overflow-hidden, and background positioning. | 0.39 | Low | Border-radius clipping, absolute positions
Home Page | Curated For You | Image Zoom Transition | SCSS card background image zoom scale animation on card hover. | 0.39 | Medium | SCSS transform scale(1.06) transition
Home Page | Curated For You | Glassmorphic Price Badge | Top-right absolute price badges styling, translucent background, backdrop-filter blur. | 0.79 | High | Backdrop-filter blur, border translucent
Home Page | Curated For You | Metadata Text Overlay | Card bottom content row, city display text, country & date metadata with text-shadow. | 0.55 | Medium | Linear gradient overlay, white text shadow
Home Page | Hidden Gems | Trending Header Badge | Trending badge next to section title, custom border-radius, background and text colors. | 0.55 | Medium | Trending Pill, color contrast, vertical alignment
Home Page | Hidden Gems | 3-Column Grid | Responsive grid layout for 3 columns (Cappadocia, Santorini, Kyoto) with equal margins. | 0.55 | Medium | Grid columns, gap wrap spacing
Home Page | Hidden Gems | Card Metadata & Emojis | Card bottom tagline details featuring custom emoji alignments (Kyoto lantern, etc.). | 0.74 | Medium | Emoji spacing, font sizes, text alignments
Home Page | Beach Escapes | Section Nav Header | Heading alignment, spacing rules, and see all link active colors. | 0.39 | Low | Flex row, title padding, link opacity hover
Home Page | Beach Escapes | 2-Column Wide Grid | Grid layout for 2 wide columns (Maldives and Seychelles) matching the aspect ratio. | 0.55 | Medium | Aspect ratio card, responsive bootstrap width
Home Page | Beach Escapes | Description Left Overlays | Positions Maldives and Seychelles descriptions absolutely in the bottom left. | 0.55 | Medium | Absolute bottom-left padding, text-shadow
Home Page | Beach Escapes | Price Card Overlay | Floating white container card structure on the right side of the escapes cards. | 0.55 | Medium | Float badge container, rounded-4, soft shadow
Home Page | Beach Escapes | Price Hover lift effect | Starting at labels, bold price number alignment, and custom lift transition on hover. | 0.79 | High | Hover translateY(-4px) animation, ease-in-out
Home Page | Newsletter Banner | Navy Panel Container | Deep navy background container layout, custom card border-radius (24px), padding. | 0.55 | Medium | Newsletter-card padding, navy base color
Home Page | Newsletter Banner | 56px Heading | Typography rules (56px bold), line-height (61.6px), letter-spacing (-1.12px). | 0.63 | High | Hanken display font, letter-spacing tracking
Home Page | Newsletter Banner | Centered Subtitle | Subtitle positioning, maximum text width (560px), and light translucent white color. | 0.39 | Low | Max-width text centering, custom color opacity
Home Page | Newsletter Banner | Translucent Input Box | Email input layout, border active state, focus shadow, and placeholder style. | 0.55 | Medium | Input focus outline shadow, border opacity color
Home Page | Newsletter Banner | Subscribe Button | Vibrant blue subscribe button layout, padding, hover background shift. | 0.39 | Medium | Btn subscribe button, hover background transitions
Home Page | Newsletter Banner | Disclaimer Footer | Disclaimer text, font size, margins, and low opacity grey layout. | 0.39 | Low | Text footer styles, opacity meta
Home Page | Feature Cards | 3-Column Responsive Grid | Bootstrap grid flex setup for three value cards with equal height alignments. | 0.39 | Medium | D-flex, flex-row column wrap
Home Page | Feature Cards | White Cards Container | Card white backgrounds, border-radius (24px), drop shadows, lift translations on hover. | 0.55 | Medium | Card shadow lift, hover translation, custom margins
Home Page | Feature Cards | Circular Icon Wrappers | Light blue circle wrappers (rgba(37, 99, 235, 0.08)), padding, align items centered. | 0.55 | Medium | Icon circles, size constraints, center flex
Home Page | Feature Cards | Inline SVG Shapes | Inline SVG custom brand shapes rendering (sparkle, price, speedometer). | 0.39 | Low | SVG xml markup, custom vector fill
Home Page | Feature Cards | Feature Texts & Typography | SemiBold headings (24px), regular description paragraph lines (16px, line-height 24px). | 0.39 | Low | Custom text weights, letter tracking
Chat & Search | Navigation & Header | Main Global Navbar | Logo image alignment, support/Explore navigation tabs, AED and login buttons. | 0.74 | Low | Header layout wrapper, logo, login active
Chat & Search | Navigation & Header | Active Link indicator | Explore blue underline active state tab styling. | 0.39 | Low | Active border tab color, layout lines
Chat & Search | Chat Area | User Bubble Layout | Right-aligned user prompt card, rounded corners, white background layout, margins. | 0.55 | Medium | Flexbox wrapper user bubble, bubble borders
Chat & Search | Chat Area | System Status Bubble | Left-aligned grey status bar bubble card, status text styling. | 0.55 | Medium | System bubble, background secondary
Chat & Search | Flight Cards | Main Wrapper Container | Rounded grey/blue wrapper container holding search outcomes, padding. | 0.39 | Low | Flight panel container border-radius
Chat & Search | Flight Cards | Emirates Card Headers | Emirates flight row logo, text details, blue circular 'FASTEST' badge. | 0.74 | Medium | Card headers grid rows, badge colors
Chat & Search | Flight Cards | EgyptAir Card Headers | EgyptAir flight row logo, text, purple/blue 'CHEAPEST' badge. | 0.74 | Medium | Card header grid, badge secondary color
Chat & Search | Flight Cards | Timeline Duration Line | Departure/arrival times (CAI/DXB), timeline graphic lines, duration meta texts. | 1.58 | High | Horizontal line SVG, dot placement, absolute layout
Chat & Search | Flight Cards | Economy & Price Footers | Economy Class text styling, bold price text value ('AED X,XXX') positioning. | 0.55 | Low | Price alignment column, display font price text
Chat & Search | Follow-up Sug. | Prompt Suggestions grid | Suggested query tags buttons flex layout directly under chat output. | 0.55 | Medium | Suggestions pill buttons row layout
Chat & Search | Follow-up Sug. | Prompt Hover States | Transitions, border, background color shifts upon query button hover. | 0.39 | Low | SCSS hover button active states
Chat & Search | Chat Input Bar | Input Container & Borders | Bottom sticky prompt search container, border outline shadow on focus. | 0.74 | Medium | Sticky input wrapper focus borders
Chat & Search | Chat Input Bar | Attachment Buttons | Paperclip SVG icon integration, Sparkle icon, and blue circular send button. | 0.74 | Medium | Attachment click indicators, send btn SVG
Auth & Login | Auth Container | Central Card Layout | Rounded white card modal layout, background screen overlay filter blur. | 0.74 | Medium | Auth modal card, absolute center wrapper
Auth & Login | Social Logins | Google Login Button | Google logo SVG integration, border grey outline, background hover state. | 0.55 | Medium | Btn Google button active hover
Auth & Login | Social Logins | Apple Login Button | Apple white SVG logo integration, dark navy styling layout, hover. | 0.39 | Low | Btn Apple button hover transition
Auth & Login | Social Logins | Facebook Login Button | Facebook SVG logo, blue brand background coloring, hover state. | 0.39 | Low | Btn Facebook button hover transition
Auth & Login | Divider & Link | Or Divider & Email | OR rule separator divider lines, 'Continue with email' blue text link. | 0.74 | Low | Horizontal divider line, email text links
Auth & Login | Footer Meta | Links & Compliance text | Join Peek action link, disclaimer with Terms & Privacy Policy anchors. | 0.74 | Low | Compliance text, anchor policy links
Legal & Support | Sidebar Nav | Legal Menu Links | Vertical sticky list, text weights, legal sidebar alignments. | 0.74 | Low | Sticky sidebar vertical list columns
Legal & Support | Sidebar Nav | Menu Active States | Active sidebar menu item styling (blue left border, bold text color). | 1.1 | Medium | Active left-border indicators, transition states
Legal & Support | Sidebar Nav | Need Help Info Card | Sidebar help container, blue background, card contents, action link buttons. | 0.74 | Medium | Help card background styling, text alignments
Legal & Support | Doc Container | Main Wrapper Layout | Card shadow padding, metabox Support > Legal > Terms of Service breadcrumbs. | 0.74 | Low | Card wrap container, support breadcrumbs links
Legal & Support | Doc Content | Numbered Lists & Typography | Document headings, numbering spacing, bold text alignments, margins. | 1.1 | Medium | Doc sections padding, heading spacing
Legal & Support | Doc Content | Checked Bullet Points | Bullet point checkmarks inside responsibilities sections, custom blue SVGs. | 1.26 | High | List-style-type none, custom check icons absolute
Legal & Support | Doc Content | Callout Blockquote Card | Quote block styling, left thick blue border, light blue highlight background. | 0.55 | Low | Callout card left thick border, HSL highlight
Legal & Support | Doc Content | Data Table Layout | Data tables grid layout, Action type, responsibility columns, fee grids. | 0.93 | Medium | Border collapse table, Action bold AED numbers
Legal & Support | Doc Footer | Was Helpful Pill Buttons | Was helpful thumbs Yes / No button pills, margins, borders, select states. | 0.55 | Medium | Pill borders, Inline SVG icons, feedback selected
Total UI Estimate